## work plan
Work package
| WP 1: User studies & Scenarios | Pilot |  | For next phase /TUDO |  |  |  |  | Final study, eval/TUDO
| WP 2: Debugging techniques |  | Both at TUDO/Graz
| WP 3: Evaluation |  |  | Corpus | Eval/Graz |  |  |  | Integr. | Eval./Both
| WP 4: Ranking heuristics |  |  |  |  | GRAZ
| WP 5: Query generation |  |  |  |  | TUDO
| WP 6: Classification & strategy selection | [6 empty] | GRAZ
|  | Year 1 |  |  | Year 2 |  | Year 3
Work packages
1 | Analysis and pilot study
2 | Debugging techniques
3 | Query generation
4 | Evaluation and Validation I
5 | Ranking heuristics
6 | Classification & strategy selection
7 | Evaluation and Validation II
|  | Year 1 |  |  | Year 2 |  | Year 3

## financials
|  |  |  | Austrian partner |  |  |  | German partner
| Year 1 | Year 2 | Year 3 |  | Year 1 | Year 2 | Year 3 |  | Year 1 | Year 2 | Year 3
Post-doc student Graz | 60610 | 60610 | 60610 | Post-doc student | 60610 | 60610 | 60610
Doctoral student Graz (20h) | 23133.3333 | 23133.3333 | 23133.3333 | Doctoral student (30h) | 34700 | 34700 | 34700 | Doctoral student | 56100 | 56100 | 56100
Doctoral student Dortmund | 56100 | 56100 | 56100 | Personnel costs | 95310 | 95310 | 95310 | Personnel costs | 56100 | 56100 | 56100
Personnel costs | 139843.3333 | 139843.3333 | 139843.3333
|  |  |  | Additional funds | 7404 | 0 | 0 | Additional funds | 1500 | 0 | 0
|  |  |  | Travel to partner org. | 7000 | 7000 | 7000 | Travel to partner org | 1000 | 1000 | 1000
Additional funds (HW/SW) | 4500 | 0 | 0 | 5% general costs | 5485.7 | 5115.5 | 5115.5 | Dissem. /travel |  | 3500 | 3500
Travel costs (German partner) | 2000 | 4000 | 4000 | Annual costs | 115199.7 | 107425.5 | 107425.5 | Annual costs | 58600 | 60600 | 60600
5% general costs (Austrian partner) | 4412.1667 | 4187.1667 | 4187.1667 | Total cost |  |  | 330050.7 | Total cost |  |  | 179800
Annual costs | 150755.5 | 148030.5 | 148030.5
Project budget |  |  | 446816.5 | [6 empty] | Total project cost | 509850.7
Limit für 3 Reviewer: 450.000 EURO
Reisen TUDO | Konferenzbesuche (Jahr 2 und 3) a 2.000 EURO
Besuche Partner (2 mal pro Jahr)
| Konferenzkosten | Anzahl
| 2000 | 2 | 4000
| Reisen zum Partner | Anzahl
| 1000 | 6 | 6000
10000